## Task Level 1
WBS | Task Name | Duration (Sample)
1 | General Conditions | 17 days
2 | Long Lead Procurement | 70 days
3 | Mobilize on Site | 10 days
4 | Site Grading and Utilities | 35 days
5 | Foundations | 33 days
6 | Steel Erection | 45 days
7 | Form and Pour Concrete - Floors and Roof | 85 days
8 | Carpentry Work | 15 days
9 | Masonry Work | 110 days
10 | Roofing | 31 days
11 | Window wall and store front closures | 60 days
12 | Building Finishes | 80 days
13 | Elevators | 40 days
14 | Plumbing | 90 days
15 | Electrical | 139 days
16 | Heating and Ventilating - AC | 180 days
17 | Final Clean-up and Occupancy | 60 days
18 | Complete Final Inspections | 6 days
19 | Complete punch list items from all inspections | 2 wks
20 | Obtain certificate of occupancy | 2 days
21 | Issue final completion documents including warranties | 1 day
22 | Issue final request for payment | 1 day

## Task Level 2
WBS | Task Name | Duration
1 | General Conditions | ?
1.1 | Receive notice to proceed and sign contract | ?
1.2 | Submit bond and insurance documents | ?
1.3 | Prepare and submit project schedule | ?
1.4 | Prepare and submit schedule of values | ?
1.5 | Obtain building permits | ?
1.6 | Submit preliminary shop drawings | ?
1.7 | Submit monthly requests for payment | ?
2 | Long Lead Procurement | ?
2.1 | Submit shop drawings and order long lead items - steel | ?
2.2 | Submit shop drawings and order long lead items - roofing | ?
2.3 | Submit shop drawings and order long lead items - elevator | ?
2.4 | Submit shop drawings and order long lead items - plumbing | ?
2.5 | Submit shop drawings and order long lead items - electric | ?
2.6 | Submit shop drawings and order long lead items - HVAC | ?
2.7 | Detail, fabricate and deliver steel | ?
3 | Mobilize on Site | ?
3.1 | Install temporary power | ?
3.2 | Install temporary water service | ?
3.3 | Set up site office | ?
3.4 | Set line and grade benchmarks | ?
3.5 | Prepare site - lay down yard and temporary fencing | ?
4 | Site Grading and Utilities | ?
4.1 | Clear and grub site | ?
4.2 | Stone site access and temporary parking area | ?
4.3 | Rough grade site (cut and fill) | ?
4.4 | Install storm drainage | ?
4.5 | Install exterior fire line and building fire riser | ?
4.6 | Perform final site grading | ?
4.7 | Erect building batter boards and layout building | ?
5 | Foundations | ?
5.1 | Excavate foundations | ?
5.2 | Excavate elevator pit | ?
5.3 | Form column piers and spread foundations | ?
5.4 | Rough-in electric and plumbing in elevator | ?
5.5 | Form elevator pit walls | ?
5.6 | Set reinforcing and anchor bolts | ?
5.7 | Pour column piers and foundations | ?
5.8 | Pour concrete elevator walls | ?
5.9 | Cure elevator wall concrete | ?
5.1 | Cure piers and foundations | ?
5.11 | Strip wall forms | ?
5.12 | Strip column piers and foundation forms | ?
5.13 | Install pneumatic tube in elevator pit | ?
5.14 | Prepare and pour concrete floor in elevator pit | ?
6 | Steel Erection | ?
6.1 | Erect steel columns, beams and joist - 1st and 2nd floors | ?
6.2 | Erect steel columns, beams and joist - 3rd floor and roof | ?
6.3 | Install miscellaneous iron and bracing - 1st and 2nd floors | ?
6.4 | Install miscellaneous iron and bracing - 3rd floor and roof | ?
6.5 | Install stairs and miscellaneous iron railing | ?
6.6 | Touch-up paint on steel | ?
7 | Form and Pour Concrete - Floors and Roof | ?
7.1 | Form 2nd floor including all floor openings | ?
7.2 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | ?
7.3 | Pour 2nd floor slab | ?
7.4 | Cure 2nd floor slab | ?
7.5 | Strip forms from 2nd floor slab | ?
7.6 | Form 3rd floor including all floor openings | ?
7.7 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | ?
7.8 | Pour 3rd floor slab | ?
7.9 | Cure 3rd floor slab | ?
7.1 | Strip forms from 3rd floor slab | ?
7.11 | Form roof slab including all floor openings | ?
7.12 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | ?
7.13 | Pour roof slab | ?
7.14 | Cure roof slab | ?
7.15 | Strip forms from roof slab | ?
7.16 | Form 1st floor | ?
7.17 | Install electrical underground | ?
7.18 | Install plumbing underground | ?
7.19 | Install rebar and in-floor utilities | ?
7.2 | Pour 1st floor slab | ?
7.21 | Cure 1st floor slab | ?
7.22 | Strip forms from 1st floor slab | ?
8 | Carpentry Work | ?
8.1 | Install exterior sheathing and metal studs | ?
9 | Masonry Work | ?
9.1 | Rough-in plumbing at toilets and masonry walls | ?
9.2 | Lay masonry at core, mechanical, and toilets | ?
9.3 | Install exterior masonry work | ?
9.4 | Install roof drains | ?
9.5 | Install tile in toilet rooms | ?
9.6 | Clean masonry | ?
9.7 | Clean toilet room tile | ?
10 | Roofing | ?
10.1 | Install flashing at parapet walls | ?
10.2 | Pour lightweight concrete roof fill | ?
10.3 | Install seamless roofing material | ?
10.4 | Spread stone ballast on seamless roof | ?
10.5 | Set rooftop equipment | ?
11 | Window wall and store front closures | ?
11.1 | Install window wall aluminum and glass | ?
11.2 | Install interior stud walls and drywall | ?
11.3 | Install interior doors and hardware | ?
11.4 | Install store front doors and hardware | ?
12 | Building Finishes | ?
12.1 | Install millwork and wood trim | ?
12.2 | Paint walls and woodwork | ?
12.3 | Install conduit at ceiling plenum space | ?
12.4 | Install duct in ceiling plenum space | ?
12.5 | Install ceiling grid | ?
12.6 | Install ceiling tile | ?
12.7 | Hang wallpaper | ?
12.8 | Install building carpet | ?
12.9 | Install hardware and accessories | ?
12.1 | Complete interior and exterior sod and plantings | ?
12.11 | Pave, curb, and stripe parking lot | ?
13 | Elevators | ?
13.1 | Set elevator equipment in shafts | ?
13.2 | Set equipment in mechanical room | ?
13.3 | Test and align doors and equipment | ?
14 | Plumbing | ?
14.1 | Rough-in plumbing in drywall walls | ?
14.2 | Tie-in fire line riser and set valves | ?
14.3 | Set plumbing fixtures and trim | ?
14.4 | Flush, test, and clean piping and fixtures | ?
15 | Electrical | ?
15.1 | Rough-in electrical in masonry walls | ?
15.2 | Rough-in electrical in drywall walls | ?
15.3 | Pull wire in conduit and set area transformers | ?
15.4 | Install and terminate electrical devices | ?
15.5 | Make electrical terminations for HVAC equipment | ?
15.6 | Install light fixtures - test and clean | ?
16 | Heating and Ventilating - AC | ?
16.1 | Set equipment in mechanical room | ?
16.2 | Rough-in mechanical in masonry walls | ?
16.3 | Rough-in mechanical in drywall walls | ?
16.4 | Install duct in building chase | ?
16.5 | Set HVAC trim and test and balance system | ?
17 | Final Clean-up and Occupancy | ?
17.1 | Install hard tile flooring in common areas | ?
17.2 | Clean hard tile floors | ?
17.3 | Remove debris from building and do final clean-up | ?
17.4 | Substantial completion date | ?
18 | Complete Final Inspections | ?
18.1 | Complete elevator inspection and certification | ?
18.2 | Perform architect's inspection | ?
18.3 | Perform local building agency inspection | ?
18.4 | Perform Fire Marshal's inspection | ?
19 | Complete punch list items from all inspections | ?
20 | Obtain certificate of occupancy | ?
21 | Issue final completion documents including warranties | ?
22 | Issue final request for payment | ?